## DVP
Efficycle 2017 Design Validation Plan
Team ID |  |  | Team Name |  |  |  |  | Target Vehicle Completion Date
17057 |  |  | AARYANS |  |  |  |  | 2017-09-20
Sr. No. | Subsystem | Part/Parameter Under Validation | Responsible | Design/Performance Requirement | Validation Method | Equipment/ Instrument used | No. of Trials/ Fequency | Validation Test Observations | Result | Remarks
1 | Braking System | Stopping Distance using all brakes | Vikas | Stopping Distance=4m (<5m as per rulebook criteria) @24km/h | Run 50m in 15 sec, stop before 5m | Measuring Tape, Stop Watch, Brake Test Track to be made as per rulebook | min 15 trials | Stopping Distance Trial 1= ……..m Trial 2=……...m Trial 3= ……..m .. .. | Max stopping distance= 3.5m
2 |  |  | Vikas | Stopping Distance <5.5m @ max speed = 30 km/h (only if top speed >24km/h) | Run 50m in 12 sec, stop before 6m | Measuring Tape, Stop Watch, Brake Test Track to be made as per rulebook | min 15 trials |  |  | Max speed =…..km/h as per design
|  | Stopping Distance using only front brakes | Vikas | Stopping Distance=6m (<5m as per rulebook criteria) @24km/h
|  | Stopping Distance using rear brake only | Vikas | Stopping Distance=5m (<5m as per rulebook criteria) @24km/h
3 |  | Brake Force Distribution | Kirti | All brakes must work at same time and vehicle should go straight during braking | Perpendicular Lines marked on track, Deviation on LH/RH <300mm | Try Square, Scale, measuring tape | min 15 trials | Offset from Straight Line Trial 1= ……..m Trial 2=……...m .. ..
4 |  |  | Kirti |  | Visual observation to check vehicle skidding | N/A | min 15 trials
| motor | speed | Nikhil | No load condition speed must be greater than 400 rpm | Motor is rotated at no load condition and speed measured by tachometer | tachometer | 2 trials
|  | current | Nikhil | No load condition current should not be exceed 2 amp | Motor is rotated at no load condition and current is measured by ammeter | ammeter | 2trials
|  | fuse | Nikhil | Fuse should melt at 16 amp | fuse of rating 20A is tested on current source device. fuse is observered to melt instantaneously at 20A. | fuse | 2 trials
|  |  | Nikhil | MCB should trip at 18 amp | MCB of rating 18A is used, which is tested in lab and trips at 22A. If fuse fails then MCB will serve as backup protection and isolate controller circuit from battery. | MCB | 2 trials
5 | Battery | Charging Time | Nikhil | Discharged battery should fully charge in <6hrs | Check Terminal Voltage before charging and after 2hrs | Multimeter, stopwatch | min 10 trials | 1. V1= …..V, V2….=V |  | V1= Voltage before plug-in V2= Voltage after 2hrs
6 |  |  | Nikhil |  | motor operation is possible only when Battery voltage is above 90 % of battery rated voltage i.e. 48V. | Multimeter, stopwatch | min 10 trials
Battery voltage
7 |  | Leakage check | Shubham | No leakage from battery in static & dynamic conditions | Tilt battery on all 4 sides by not more than 45deg, hold for 10 sec and observe any leakage | Stopwatch | Min 3 trials |  |  | Do not touch bare hand and use safety precautions, gloves, goggles, shoes, metal trays etc
8 |  |  | Shubham |  | Check battery each time when vehicle runs >1km | N/A | Min 3 trials |  |  | Don’t touch battery, take photos etc
9 | Dimension | Length | Prasad | Length= 2015mm | Check length b/w front & rear projected parts | Plumb bob, measuring tape | One time
10 |  | Width | Prasad | Width= 1230mm | …….. | Plumb bob, measuring tape | One time
|  | Height | Prasad | Height= | Measure hight from ground | Measuring Tape | one time
11 |  | Seat Height | Prasad | Seat Height at Point A=….. | ……… | Scale/ measuring tape | One time
12 |  | Sitting Space Height | Prasad | Sitting Space height=…… | ……… | Scale/ measuring tape, spirit level | One time
|  | Ground clearance | Prasad | Moving part should be 3 inch | measure ground clearance of paddles | Measuring tape | one time
|  | Ground clearance | Prasad | rigid members should be 6 inch | measure ground clearance of steering member | Measuring tape | one time
|  | Seatbelt height | prasad | Seatbelt height from shoulder is 4 inch |  | Measuring Tape | one time
|  | Head rest | prasad | Should be 1 inch above head | Measure distance from head to headrest | Mesuring Tape | one time
|  | Seat Inclination | Prasad | Seatback angle=…..deg | ……….. | Inclinometer | One time
|  | Overhead protection extension | Prasad | extension>=12 inch(rulebook)
13 | Clearance | body clearance from moving part | prasad | body part should be 3inch from front wheel | Measuring distance after driver sits on seat | measuring tape | one time
|  | body clearance between two drivers | prasad | body part should be 3inch from each other | distance is calculated after two drivers sit in position | Measuring tape
|  | paddle clearance | prasad | paddle distance should be 3 inch | measure distance between two paddles | Measuring tape | one time
| Frame | critical Weld Quality | prateek | critical points of the frame should not have minor cracks | critical points are checked bydye penetration test | dye penetrant,developer, cleaning agent | After 10 practices
14 |  | Weld Quality | Suraj | No Cracks should be present at the frame members & weld joints | visible inspection of all frame members & steering joints (One Time) | N/A | One time
15 |  | Weight | Sanket | less than 150 kg (by rulebook) | Measure weight by device | Measuring machine | one time
| Utility box | Length | bhavika | >16 inch | check length internally | Measuring Tape | One time
|  | Height | Bhavika | >8 inch | check length internally | Measuring Tape | One time
|  | width | bhavika | >12 inch | check length internally | Measuring Tape | One time
| Fastners | theads | suraj | at least 2 theads should be visible after locking | visible inspection | N/A | one time
|  | locking | sanket | Fastners should not get loose during running | Check fastners after vehicle running | Torque Wrench | every 2km
15 | Wheels | Load Bearing Capacity | Chandrashekar | Wheels should not bend during running | Check wheel conditions visually after vehicle running with 2 heaviest drivers and 20kg payload | 20kg payload, weighing machine | every 2km
|  | Axle shearing strength | chandrashekhar | axle should not bend at steady and dynamic conditions | check tensile strength on UTM machine and then fix the shearing strength | Universal Testing Machine | one time
|  | Wheels rotation inside bearing | Bhavika | They should move smoothly inside bearing | Before eeach practice chech the ccondition of bearing | Visual Inspection | Before every run
|  | Camber angle of front wheels | Bhavika | Camber angle of each wheel should be same | Lift the front sideof vehicle to measure the camber angle | Visual Inspection | Before every run
16 | Steering | Joints | suraj | All Joints must be smooth and remain so while working | Handle is turned in steady position and smothness is checked | Visual Inspection | Before every run
17 |  | Tie rod | sanket | Tie rod must not bend under dynamic loads | check the linarity of tie rod in all planes after each practice | Visual inspection after each practice | After 19 practices
|  | Checking of minimum turning radius for both wheels | sachin | Turning Radius for Inner and outer wheel must be less than 2 m and 4m resp. | Concentric circles of radii 2m and 4m are marked | measuring tape and chalkpit. | 10 trials per day
|  | Figure of 8 Test | sachin | Turning Radius for Inner wheel must be less than 2 m | Figure of 8 track is drawn on ground as per rulebook | chalkpit , measuring tape, | 10 trials per day
|  | Steering movement at static condition | sachin | Maximum loaded condition wheels should turn easily and completely | Two drivers and payload is applied and at static position turning of wheels is checked | Visual Inspection | 3 trials per day
| Transmission | manual max. speed | prateek | Maximum speed for manual transmission must be more than 20 kmph | vehicle is run on straight road and then speed is calculated using app | mobile, app | 8 km every day
|  | electric max. speed | prateek | maximum speed for electric transmission must be more than 25 kmph |  |  | 5 km every day
|  | hybrid max. speed | prateek | maximum speed for hybrid transmission must be more than 30 kmph |  |  | 10 km every day
|  | manual drive gradeability | prateek | >10 degrees | slope of 15 degrees must be crossed by manual drive | ____ | min1 trial per day
|  | hybrid drive gradeability | prateek | >15 degrees | slope of 20 degrees must be crossed by hybrid drive | ____ | min2 trial per day
|  | chain tension | Nikhil | tension in all chains remains constant | chain tension is tested before and after every testing | Visual Inspection | Twice in a day
|  | shaft | Bhavika | should not undergo any deflection | Visual Inspection | ______ | Before and after each practice
|  | Acceleration test(manual) | bhavika | 100 m within 20sec | 100m distance is marked and time to cross is measured | marking chalk,Measuring tape,Stopwatch | once in day
|  | Acceleration test(Hybrid) | bhavika | 100 m within 15 sec | 100m distance is marked and time to cross is measured | marking chalk,Measuring tape,Stopwatch | once in day

## checkpoints
No | parameter |  | Y/N
1 | Front impact member
2 | side impact member
3 | rear impact member
4 | rollover protection
5 | removable front fairing
6 | removable seats
7 | Three point seat belt
8 | Seat belt coming from above the driver shoulder
9 | body clearance>3 inch
10 | ground clearance >6 inch
11 | chain protection
12 | on board charging mechanism of battery
13 | individual break to each wheel
14 | steering clearance
15 | utility box
16 | proper routing of wires
17 | Provision of kill switch
18 | metric gradeM 8.8 bolts
19 | use of all Nylock nuts
20 | exposure of two treads
21 | Driver eqipments | Helmet
Knee pads
elbow pads
shin guard
22 | Sharp edges

## checksheet manual
Checksheet(manual testing)
A)Before run
| 1 | wheel camber | Both the front wheels have same camber angle
| 2 | chain tension | all the chains are having correct tension
| 3 | steering joints | all the steering joints are tight and do not have any play
| 4 | brakes | all the brakes are working when the vehicle is suspended
| 5 | steering efforts | the wheels can be turned easily when vehicle is standstill
| 6 | seat belts | the seat belt centrifugal locking is working correctly
| 7 | air pressure | the air pressure in all the tyres is sufficient
C)During run
| 1 | Wobling of wheeels | front wheels are not wobbling due to loosening of steering joints
| 2 | chain tension | the chains are not dropping while vehicle is running
| 3 | steering efforts | the steering effort is less while driving
B)After run
| 1 | wheel camber | both front wheels have same camber angle
| 2 | chain tension | the tension in all chains is correct
| 3 | steering joints | all the steering joints are tight and locked
| 4 | brakes | brakes are working properly and the shoes not touching wheel or disc
| 5 | wheel alignment | all the wheels are rotating in perfect alignment
| 6 | air pressure | air pressure in all tyres has not significantly reduced
| 7 | tyres | all the tyres are intact and fit for the next run

## checksheet hybrid
Checksheet(hybrid testing)
A)Before run
| 1 | wheel camber | Both the front wheels have same camber angle
| 2 | chain tension | all the chains are having correct tension
| 3 | steering joints | all the steering joints are tight and do not have any play
| 4 | brakes | all the brakes are working when the vehicle is suspended
| 5 | steering efforts | the wheels can be turned easily when vehicle is standstill
| 6 | seat belts | the seat belt centrifugal locking is working correctly
| 7 | motor sprocket alignment | The motor sprocket is aligned properly to wheel sprocket.This is checked by rotating the motor at full speed while wheel is suspended
| 8 | current check | current in curcuit not exceed 2 A in no load condition at full trottle
| 9 | kill switch check | the circuit should break instantaniously when kill switch is pressed
| 10 | air pressure | the air pressure in all the tyres is sufficient
C)During run
| 1 | Wobling of wheeels | front wheels are not wobbling due to loosening of steering joints
| 2 | chain tension | the chains are not dropping while vehicle is running
| 3 | steering efforts | the steering effort is less while driving
| 4 | current | the current in circuit should not exceed 12 A in steady state
| 5 | fuse check | 16A fuse in the circuit is not melted
B)After run
| 1 | wheel camber | both front wheels have same camber angle
| 2 | chain tension | the tension in all chains is correct
| 3 | steering joints | all the steering joints are tight and locked
| 4 | brakes | brakes are working properly and the shoes not touching wheel or disc
| 7 | wheel alignment | all the wheels are rotating in perfect alignment
| 8 | air pressure | air pressure in all tyres has not significantly reduced
| 9 | tyres | all the tyres are intact and fit for the next run