## 1. Project Plan
Efficycle 2017 Project Plan |  |  |  | Team ID |  | 17057 |  |  |  |  | Legends |  |  | Main Task/ Activity
Sub Task/ Activity
|  |  |  | Team Name |  | AARYANS | [7 empty] | Milestone
Milestone Details
Task ID | Task/Activity Description | Duration (Days) | Start Date | End Date | Responsible | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October
[6 empty] | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44
[6 empty] | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30
A | Team Selection and PreStudy | 30 | 2017-05-11 | 2017-06-09 | Prof. A.U. Paranjpe
A.1 | Announcement For Team Formation | 2 | 2017-05-11 | 2017-05-12 | Prof. A.U. Paranjpe & Prashant
A.2 | Preparation For Interview | 7 | 2017-05-13 | 2017-05-19 | Prashant
A.3 | Interview | 3 | 2017-05-19 | 2017-05-21 | Prof. A.U. Paranjpe & Prashant
A.4 | Team Registration | 3 | 2017-05-22 | 2017-05-24 | Prateek
A.5 | Study Of Rulebook 2016 | 5 | 2017-05-25 | 2017-05-29 | Vikas
A.6 | Study Of Different System | 11 | 2017-05-30 | 2017-06-09 | Prasad
B | Preliminary Work | 13 | 2017-06-10 | 2017-06-22 | Prateek
B.1 | Study Of Rulebook | 5 | 2017-06-10 | 2017-06-14 | Vikas
B.2 | Departmentation Of Work | 1 | 2017-06-15 | 2017-06-15 | Bhavika & Kirti
B.3 | Preparation Of Project Plan | 5 | 2017-06-16 | 2017-06-20 | Chandrashekhar
B.4 | Discussion Of Design Targets | 4 | 2017-06-19 | 2017-06-22 | Sachin
B.5 | Submission of Project Plan | 1 | 2017-06-23 | 2017-06-23 | Prateek
C | Designing | 28 | 2017-06-23 | 2017-07-20 | Prasad
C.1 | Hand Sketch Preparation | 6 | 2017-06-23 | 2017-06-28 | Chandrashekhar
C.2 | CAD/Modeling | 9 | 2017-06-27 | 2017-07-05 | Prasad
C.3 | CAE Analysis | 9 | 2017-07-03 | 2017-07-11 | Prateek
C.4 | Cost & Weight Optimisation | 5 | 2017-07-09 | 2017-07-13 | Suraj
C.5 | Preparation Of Fabrication Plan | 6 | 2017-07-12 | 2017-07-17 | Sanket
C.6 | Preparation and Submission of reports of CAD/CAE | 2 | 2017-07-17 | 2017-07-18 | Prasad
C.7 | Preparation and Submission of reports of Fabrication plan | 2 | 2017-07-19 | 2017-07-20 | Sanket
D | Procurement | 6 | 2017-07-21 | 2017-07-26 | Suraj
D.1 | Frame Material | 5 | 2017-07-21 | 2017-07-25 | Prasad
D.2 | Transmission Accessories | 5 | 2017-07-21 | 2017-07-25 | Prateek
D.3 | Motor & Controller Unit | 6 | 2017-07-21 | 2017-07-26 | Nikhil & Shubam
D.4 | Suspension | 3 | 2017-07-24 | 2017-07-26 | Sanket
D.5 | Steering | 3 | 2017-07-24 | 2017-07-26 | Sachin
D.6 | Other Accessories | 3 | 2017-07-24 | 2017-07-26 | Bhavika & Kirti
E | Fabrication | 30 | 2017-07-27 | 2017-08-25 | Sanket
E.1 | Material Testing & Analysis | 3 | 2015-07-27 | 2017-07-29 | Bhavika & Kirti
E.2 | Frame Building | 20 | 2015-07-30 | 2017-08-17 | Suraj
E.3 | Mounting Of Wheels,Pedals | 1 | 2017-08-18 | 2017-08-18 | Chandrashekhar
E.4 | Mounting Of Steering System | 2 | 2017-08-18 | 2017-08-19 | Sachin
E.5 | Mounting Of Transmission And Braking System | 3 | 2017-08-20 | 2017-08-22 | Prateek & Vikas
E.6 | Mounting Of Motor ,Battery and Completion Of Electrical Systems | 3 | 2017-08-21 | 2017-08-23 | Nikhil& Shubham
E.7 | Mounting of Other Accessories such as Mudguard, Chain guard | 2 | 2017-08-23 | 2017-08-24 | Nikhil
E.8 | Asthetic Work And Vehicle On Road | 3 | 2017-08-23 | 2017-08-25 | Shubham
E.9 | Preparation and Submission of reports of Design | 1 | 2017-08-24 | 2017-08-25 | Parteek
F | Testing And Modification | 14 | 2017-08-26 | 2017-09-08 | Vikas
F.1 | Performance Test And Efficiency Test | 2 | 2017-08-26 | 2017-08-27 | Shubham & Prateek
F.2 | Modification And Retesting | 6 | 2017-08-27 | 2017-09-01 | Nikhil & Prasad
F.3 | Competition Based Testing, Modification and Retesting | 7 | 2017-08-02 | 2017-09-08 | Sachin& Chandrashekhar
F.4 | Design Validation Plan Preparation and Submission | 4 | 2017-09-04 | 2017-09-07 | Prasad
Text
Design Ready
Design Ready
Vehicle Ready For Compitition

## 2. Design Targets
Peformance Targets for Efficycle 2017
Sr. No. | Items | Details
1 | Team ID | 17057
2 | Team Name | AARYANS
3 | Kerb Weight (kg): | 97
4 | Length (mm): | 2336.8
5 | Length (inch): | 92"
6 | Width (mm): | 1397
7 | Width (Inch): | 55"
8 | Height (mm): | 1651
9 | Height (inch): | 65"
10 | Max speed (km/h): | 38
11 | Maximum acceleration (m/s2): | 0.6
12 | Grade-abilit (degree): | 6
13 | Turning radius (m): | 2.5
14 | Turning radius (inch): | 98.4"
15 | Battery Runtime (Minutes): | 180