## Plan
Efficycle 2017 Fabrication Plan |  |  |  | Team ID |  | 17057 |  |  | Legends |  |  | Delivery Period
Fabrication/ Assembly
|  |  |  | Team Name |  | AARYANS | [5 empty] | Milestone
Milestone Details
Sr. No. | Part/ Component/ Material | Lead Time for Delivery (Days) | Lead Time for Manuf. (Days) | Date of Order | Date of Delivery | Date of Manuf./ Assembly | Responsible | July |  |  |  |  | August |  |  |  | September |  |  |  | October
[8 empty] | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44
[8 empty] | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30
1 | Frame | 6 | 20 | 2017-07-21 | 2017-07-27 | 2017-08-16 | Suraj&Prasad
2 | Seat | 10 | 11 | 2017-07-27 | 2017-08-06 | 2017-08-17 | Prateek
3 | Steering Assembly | 8 | 20 | 2017-07-23 | 2017-07-31 | 2017-08-20 | Sachin&Kirti
4 | Front Suspension | 5 | 15 | 2017-07-23 | 2017-07-28 | 2017-08-12 | Sanket
5 | Wheel & Tyres | 5 | 15 | 2017-07-23 | 2017-07-28 | 2017-08-12 | Chandrashekhar
6 | Rear Suspension | 6 | 12 | 2017-08-01 | 2017-08-07 | 2017-08-19 | Suraj
7 | Braking System | 8 | 18 | 2017-07-27 | 2017-08-04 | 2017-08-22 | Vikas
8 | Human Drive Train | 8 | 20 | 2017-07-26 | 2017-08-03 | 2017-08-23 | Prateek&Prasad
9 | Electric Drive Train | 22 | 13 | 2017-07-21 | 2017-08-09 | 2017-08-22 | Nikhil&Shubham
10 | Fairing & Drive Train Protection | 8 | 14 | 2017-08-02 | 2017-08-10 | 2017-08-24 | Prasad
11 | Utility Box | 5 | 6 | 2017-08-12 | 2017-08-17 | 2017-08-23 | Bhavika
12 | Seat Belts | 6 | 8 | 2017-08-04 | 2017-08-10 | 2017-08-18 | Kirti
13 | Kill Switches | 5 | 6 | 2017-08-13 | 2017-08-18 | 2017-08-24 | Shubham&Nikhil
14 | Body Panels | 4 | 6 | 2017-08-12 | 2017-08-16 | 2017-08-22 | Prasad
15 | Under body Sheet | 6 | 8 | 2017-08-10 | 2017-08-16 | 2017-08-24 | Vikas&Chandrashekhar
16 | Identification Numbers | 5 | 2 | 2017-08-16 | 2017-08-21 | 2017-08-23 | Shubham
17 | Identification Flag | 6 | 2 | 2017-08-16 | 2017-08-22 | 2017-08-24 | Shubham
18 | Innovation | 10 | 24 | 2017-07-21 | 2017-07-31 | 2017-08-24 | Prateek&Nikhil
19 | Miscellaneous items | 7 | 9 | 2017-08-07 | 2017-08-14 | 2017-08-23 | Chandrashekhar &Sanket
20 | Paint & Final Assembly | 2 | 4 | 2017-08-19 | 2017-08-21 | 2017-08-25 | Bhavika&Kirti
Formulas:
Date of Delivery = IF(OR([Lead Time for Delivery (Days)]="",[Team ID]=""),"",[Team ID]+[Lead Time for Delivery (Days)])
AARYANS = IF(OR([Lead Time for Manuf. (Days)]="",[Date of Delivery]=""),"",[Date of Delivery]+[Lead Time for Manuf. (Days)])
Text
Frame Ready
Innovations Ready
Ready for Testing

## 1.Purchased Parts
FABRICATION PLAN
Sheet-1 : List of Parts Purchased from Market and Used Without Modification
Team Name: |  | AARYANS | Team ID: | 17057
Sr. No. | Description of Part/ Component |  | Quantity | Unit
1 | Disc brake with accessories |  | 2 | Set
2 | Brake Lever |  | 3 | Nos
3 |  | Rear Wheel | 1 | Nos
4 | Chain wheel 44 teeth |  | 2 | Nos
5 | Chain wheel crank |  | 2 | Nos
6 | Pedal |  | 2 | Pair
7 | Free Wheel |  | 4 | Nos
8 |  | Regular Chain | 4 | Nos
9 | Three speed chain wheel |  | 1 | Nos
10 | cotter pin |  | 4 | Nos
11 |  | Indicator | 2 | Nos
12 | Kill Switch |  | 1 | Nos
13 | Deraileur |  | 1 | Nos
14 | Paint |  | 250 | gm
15 | Rear view mirror |  | 2 | Pair
16 | Chain Guard |  | 2 | Nos
17 | Front suspension |  | 2 | Nos
18 | Ball Bearing |  | 2 | Nos
19 | Throttle/Acceleraor |  | 1 | Nos
20 |  | Ball Joints | 2 | Nos
21 | Eye Bolts |  | 2 | Nos
22 | Shoe Break |  | 1 | Nos

## 2.Customized Parts
FABRICATION PLAN
Sheet-2 : List of Parts Purchased from Market and Customized
Team Name: |  | AARYANS | Team ID: | 17057
Sr. No. | Description of Part/ Component |  | Quantity | Unit
1 | Shaft |  | 1 | Nos
2 | Mud Guard |  | 2 | Nos
3 | Body Panels |  | 2 | Nos
4 | under body sheets |  | 1 | Nos
5 | PVC hollow Pipes |  | 2 | Nos
6 | Front lights |  | 2 | Nos
7 | Digital Speedometer |  | 1 | Nos

## 3.Fabricated Parts
FABRICATION PLAN
Sheet-2 : List of Parts Fabricated In-House from Raw Material
Team Name: |  | AARYANS | Team ID: | 17057
Sr. No. | Description of Part/ Component |  | Quantity | Unit
1 | Free wheel hub |  | 2 | Nos
2 | Steering system |  | 1 | Nos
3 | Seat |  | 2 | Nos
4 | Chassis |  | 1 | Nos
5 | Electric Control box |  | 1 | Nos
6 | Front Suspension Support |  | 2 | Nos

## 4.Reused Parts
FABRICATION PLAN
Sheet-2 : List of Parts Re-used from Previous Seasons
Team Name: |  | AARYANS | Team ID: | 17057
Sr. No. | Description of Part/ Component |  | Quantity | Unit
1 | Wheel 20 inch |  | 2 | Nos
2 | Seat belt |  | 2 | Nos
3 | Battery |  | 1 | Nos
4 | Motor |  | 1 | Nos
5 | Rear Suspension |  | 1 | Nos
6 | Mud Guard |  | 1 | Nos
7 | Controller |  | 1 | Nos
12
13
14